## Introduction
Project Name | https://us.shein.com/
Client | Shein
Reference Document | Application URL (BRS Document not provided)
Created By | Balakumaran
Creation Date | Feb 11, 2024
Approval Date

## Test Scenario
Test Scenario | Test Scenario ID | Test Scenario URL | Test Scenario Description | Number of Test Cases Passed | Number of Test Cases Fail | Number of Test Cases Blocked | Total Number of Test Cases
Sign up | TS_001 | Application URL | Verify the working of Register Account functionality | 18 | 3 | 0 | 21
Log in | TS_002 | Application URL | Verify the working of login functionality | 14 | 2 | 0 | 16
Log out | TS_003 | Application URL | Verify the working of Log out functionality | 10 | 1 | 0 | 11
Home Page | TS_004 | Application URL | Verify the working of Home Page functionality | 13 | 0 | 0 | 13
Search | TS_005 | Application URL | Verify the working of Searching functionality | 16 | 3 | 0 | 19
Forgot Password | TS_006 | Application URL | Verify the working of Forgot Password functionality | 18 | 3 | 1 | 22
My Account | TS_007 | Application URL | Verify the working of My Account functionality | 24 | 0 | 0 | 24
Address Book | TS_008 | Application URL | Verify the working of Address Book functionality | 19 | 1 | 0 | 20
WishList | TS_009 | Application URL | Verify the working of Wish List functionality | 23 | 1 | 0 | 24
Add To Cart | TS_010 | Application URL | Verify the working of Add to Cart functionality | 10 | 0 | 0 | 10
Product Details | TS_011 | Application URL | Verify the working of Add to Cart functionality | 16 | 1 | 0 | 18
Checkout | TS_012 | Application URL | Verify the working of Checkout functionality | 19 | 0 | 0 | 19
Contact Us | TS_013 | Application URL | Verify the working of Contact Us functionality | 18 | 2 | 0 | 20
Customer Service | TS_014 | Application URL | Verify the working of Company information functionality | 10 | 0 | 0 | 10
Global | TS_015 | Application URL | Verify the working of Global functionality | 10 | 1 | 0 | 11

## Test Execution Report
TEST CASE REPORT
Project Name | SHEIN ¦ E-commerce
Module Name | Test Scenario
Feature
Test Case Version
Executed By | Balakumaran
Written By | Balakumaran
Reviewed By
TEST EXECUTION REPORT
Test Case | Pass | Fail | Not Executed | Out of Scope | Total
Test Case | 239 | 19 | 1 | 0 | 259

## Bug Report
Bug Reporting | Bug Reporting
# SL 01 | # SL 02
Issue: User cannot sign up using Facebook Account | Issue: Account cannot be verified by email
Reproducing Steps: | Reproducing Steps:
1. Go to signup page 2. Click sign up using facebook 3. Provide all the mandatory information | 1. Go to signup page 2. Fill all necessary information and sign up 3. Go to email inbox and click on the confirmation email
Environment : Production | Environment : Production
Module: Sign up | Module: Sign up
Priority: Medium | Priority: Medium
Severity: Minor | Severity: Major
Screenshot: Facebook Sign up error | Screenshot: Can't verify account by email
Expected: User should be able to signup through Facebook | Expected: Account should be verified by the email that is sent to the user
Responsible QA: Balakumaran | Responsible QA: Balakumaran
Bug Reporting | Bug Reporting
# SL 03 | # SL 04
Issue: No alert messages are displayed when any mandatory field information are not provided | Issue: Keyboard tab funtionality not working during sign up process
Reproducing Steps: | Reproducing Steps:
1. Go to signup page 2. Do not fill up the mandatory fields 3. Click "Sign up" | 1. Go to signup page 2. Use tab button to navigate from one field to another
Environment : Production | Environment : Production
Module: Sign up | Module: Sign up
Priority: Low | Priority: Low
Severity: Minor | Severity: Minor
Screenshot: No alert messages | Screenshot: No effect of Tab button
Expected: Alert messages should be displayed while tring to signup without mandatory information | Expected: User should be able to use tab to go from one field to another
Responsible QA: Balakumaran | Responsible QA: Balakumaran
Bug Reporting | Bug Reporting
# SL 05 | # SL 06
Issue: Log in page not showing proper warning messages | Issue: If the location is changed user cannot log into their account, instead they are taken to the signup page
Reproducing Steps: | Reproducing Steps:
1. Go to login page 2. Input no credentials 3. Click on log in | 1. Go to the login page 2. Change the location 3. Input valid credentials and log in
Environment : Production | Environment : Production
Module: Log in | Module: Log in
Priority: Medium | Priority: Medium
Severity: Minor | Severity: Minor
Screenshot: No error messages | Screenshot: Location change error
Expected: Log in page should display proper warning messages | Expected: User should be able to sign in even after changing location
Responsible QA: Balakumaran | Responsible QA: Balakumaran
Bug Reporting | Bug Reporting
# SL 07 | # SL 08
Issue: When searching for a non-existing product, instead of showing no products, irreleveant products are shown | Issue: User not getting logged out from all devices after logging out
Reproducing Steps: | Reproducing Steps:
1. Enter non existing product name into the 'Search' text box field 2. Click on the button having search icon | 1. Click on 'My Account' Dropmenu in Firefox Browser 2. Select 'Logout' option 3. Perform any operation which requires the user to log, like going to the my account page
Environment : Production | Environment : Production
Module: Search | Module: Log out
Priority: Medium | Priority: Medium
Severity: Minor | Severity: Minor
Screenshot: Irrelevant products are shown | Screenshot: User logged in
Expected: The message "No products" should be displayed | Expected: User should be logged out of all devices
Responsible QA: Balakumaran | Responsible QA: Balakumaran
Bug Reporting | Bug Reporting
# SL 09 | # SL 10
Issue: Serching without writing anything inside the searchbox shows random results | Issue: Keyboard tab funtionality not working properly in the search items page
Reproducing Steps: | Reproducing Steps:
1. Don't enter anything into the 'Search' text box field 2. Click on the button having search icon | Press Tab and Enter keys to perform Search operation and select several options in the Search page
Environment : Production | Environment : Production
Module: Search | Module: Search
Priority: Medium | Priority: Medium
Severity: Minor | Severity: Minor
Screenshot: Random product are shown | Screenshot: Not Applicable
Expected: 'There is no product that matches the search criteria' should be displayed in the Search Results page | Expected: User should be able to use tab to go from one field to another
Responsible QA: Balakumaran | Responsible QA: Balakumaran
Bug Reporting | Bug Reporting
# SL 11 | # SL 12
Issue: Placeholder text is not displayed in the e-mail address field of the forgot password page | Issue: No breadcrumb is shown of the forgot password page
Reproducing Steps: | Reproducing Steps:
1. Click on 'Forgotten Password' link from Login page 2. Check Placeholder text for 'E-Mail' Address field | 1. Click on 'Forgotten Password' link from Login page 2. Check the working of Breadcrumb
Environment : Production | Environment : Production
Module: Forgot Password | Module: Forgot Password
Priority: Medium | Priority: Medium
Severity: Minor | Severity: Minor
Screenshot: No placeholder | Screenshot: No breadcrumb
Expected: Proper Placeholder text should be displayed inside the 'E-Mail Address' fields of the 'Forgotten Password' page | Expected: Proper breadcrumb should be displayed
Responsible QA: Balakumaran | Responsible QA: Balakumaran
Bug Reporting | Bug Reporting
# SL 13 | # SL 14
Issue: The password visibility of the password and confirm password fields is not present | Issue: The default address gets deleted directly without any warning to create a new default address if the user tries to delete it
Reproducing Steps: | Reproducing Steps:
1. Click on the reset password link available in the email 2. Enter any text into 'Password' and 'Confirm' fields on the 'Reset your Password' page | 1. Click on 'Address Book' option 2. Click on 'Delete' button of the default address displayed in the 'Address Book Entries' page
Environment : Production | Environment : Production
Module: Forgot Password | Module: Address Book
Priority: Medium | Priority: Medium
Severity: Minor | Severity: Minor
Screenshot: No password visibility toggling | Screenshot: Address gets deleted
Expected: User should be able totoggle password visibility for security purposes | Expected: The default address should not be allowed to be deleted until a new default address is created
Responsible QA: Balakumaran | Responsible QA: Balakumaran
Bug Reporting | Bug Reporting
# SL 15 | # SL 16
Issue: User cannot put products to wishlist directly from the search results page | Issue: No options for the user to like, tweet or share thier favorite products to social media platforms
Reproducing Steps: | Reproducing Steps:
1. Enter any existing Product name into the Search text box field 2. Click on the button having search icon 3. Click on 'Add to Wish List' option of a product that is dispayed in the 'Search Results' page | 1. Go to any product details page 2. Check if sharing to social media option is available
Environment : Production | Environment : Production
Module: Wishlist | Module: Sign up
Priority: Medium | Priority: Medium
Severity: Minor | Severity: Minor
Screenshot: No option to add products to wishlist | Screenshot: No social media buttons
Expected: User should be able toput products to wishlist directly from the search results page | Expected: User should be able to like and share their favorite products to social media platforms
Responsible QA: Balakumaran | Responsible QA: Balakumaran
Bug Reporting | Bug Reporting
# SL 17 | # SL 18
Issue: User is not able to change their reactions to the answers once they have already provided a reaction | Issue: When hovering over the example questions, the same question pops up once again
Reproducing Steps: | Reproducing Steps:
1. Go to the customer care page 2. In the FAQ section click in view more 3. In the support page click on the like or dislike button | 1. Go to the customer care page 2. Click on the customer service button. 3. Click on any of the questions 4. Check the UI of the page
Environment : Production | Environment : Production
Module: Contact Us | Module: Contact Us
Priority: Medium | Priority: Medium
Severity: Minor | Severity: Minor
Screenshot: Reactions can't be changed | Screenshot: UI issue
Expected: User should be able to change their reactions to the answers even after they have already provided a reaction | Expected: User should be able to signup through Facebook
Responsible QA: Balakumaran | Responsible QA: Balakumaran
Bug Reporting
# SL 19
Issue: User cannot return to the US version of the website once they have nagigated to the international version
Reproducing Steps:
1. Go to the global icon on the home page 2. Click the US site link
Environment : Production
Module: Global
Priority: Medium
Severity: Minor
Screenshot: No change back option
Expected: User should be able to return to the US version of the website
Responsible QA: Balakumaran

## Sign up
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Bug Screenshot | Comments
<< Test Scenarios
TC 001 | (TS_001) Sign up Functionality | Checking the Sign up page for spelling or grammatical mistakes | Go to the webpage url https://us.shein.com/ | 1. Go to the website url 2. Navigate to signup page 3. Check for spelling or grammatical errors | Not Applicable | There should not be any spelling or grammatical errors | Found as expected | P1 | PASS
TC 002 | (TS_001) Sign up Functionality | Verify the proper UI of the webpage adhering to the srs document | Go to the webpage url https://us.shein.com/ | 1. Go to the website url 2. Navigate to signup page 3. Check the interface of the website adhering to the srs document | Not Applicable | The UI should be properly built according to the srs document | Found as expected | P3 | PASS
TC 003 | (TS_001) Sign up Functionality | Verify the mandatory fields are marked with an asterisk | Go to the webpage url https://us.shein.com/ | 1. Go to signup page 2. Check if the mandatory fields has an asterisk next to them | Not Applicable | The mandatory fields should have an asterisk next to them | Found as expected | P1 | PASS
TC 004 | (TS_001) Sign up Functionality | Verify the checkbox beside "I agree to privacy terms" | Go to the webpage url https://us.shein.com/ | 1. Go to signup page 2. Check if there is a checkbox beside "I agree to privacy terms" | Not Applicable | There should be a checkbox beside "I agree with privacy terms" | Found as expected | P2 | PASS
TC 005 | (TS_001) Sign up Functionality | Verifying if multiple checkboxes can be selected in "Style Preferences" | Go to the webpage url https://us.shein.com/ | 1. Go to signup page 2. Check several checkboxes in style preference | Not Applicable | Several checkboxes can be selected in style preference | Found as expected | P3 | PASS
TC 006 | (TS_001) Sign up Functionality | Checkbox beside "Agreeing to receive newsletter" works correctly | Go to the webpage url https://us.shein.com/ | 1. Go to signup page 2. Check if the checkbox "Agreeing to receive newsletter" works correctly | Not Applicable | User should be able to check or uncheck the checkbox | Found as expected | P4 | PASS
TC 007 | (TS_001) Sign up Functionality | Verify registering an account by only putting mandatory fields | Go to the webpage url https://us.shein.com/ | 1. Go to signup page 2. Only put in the mandatory fields 3. Click "Sign up" | Not Applicable | User should be registered to the website | Found as expected | P5 | PASS
TC 008 | (TS_001) Sign up Functionality | Verify registering an account by not putting any mandatory fields | Go to the webpage url https://us.shein.com/ | 1. Go to signup page 2. Fill up all fields except the mandatory ones | Not Applicable | User should not be allowed to register | Found as expected | P6 | PASS
TC 009 | (TS_001) Sign up Functionality | Verify alert messages are displayed when any mandatory field information are not provided | Go to the webpage url https://us.shein.com/ | 1. Go to signup page 2. Do not fill up the mandatory fields 3. Click "Sign up" | Not Applicable | Proper alert messages should be displayed | No alert messages are displayed | P7 | FAIL
TC 010 | (TS_001) Sign up Functionality | Verifying registration doesn't work without checking the "I agree to privacy terms" checkbox | Go to the webpage url https://us.shein.com/ | 1. Go to signup page 2. Provide necessary information to all the fields 3. Check if the webpage allows to signup without checking the "I agree to privacy terms" checkbox | Not Applicable | User should not be able to register without checking the "I agree to privacy terms" checkbox | Found as expected | P8 | PASS
TC 011 | (TS_001) Sign up Functionality | Checking by inputting invalid email format | Go to the webpage url https://us.shein.com/ | 1. Go to signup page 2. Input invalid email format | hello@world | User should not be able to sign up and shown an error message | Found as expected | P9 | PASS
TC 012 | (TS_001) Sign up Functionality | Checking by inputting a password that doesn't meet the requirements | Go to the webpage url https://us.shein.com/ | 1. Go to signup page 2. Input a password that doesn't meet the requirements of the website | Not Applicable | User should not be able to sign up | Found as expected | P10 | PASS
TC 013 | (TS_001) Sign up Functionality | Verify the password values are hidden | Go to the webpage url https://us.shein.com/ | 1. Go to signup page 2. Input the password 3. Check if the password values are hidden | Not Applicable | The password values should be hidden | Found as expected | P11 | PASS
TC 014 | (TS_001) Sign up Functionality | Check by inputing invalid combinations of characters in password and confirm password field | Go to the webpage url https://us.shein.com/ | 1. Go to signup page 2. Input the password 3. Input a different password in the "confirm password" field | Not Applicable | User should not be able to register | Found as expected | P12 | PASS
TC 015 | (TS_001) Sign up Functionality | Check the toggle button beside the password input field for visibility | Go to the webpage url https://us.shein.com/ | 1. Go to signup page 2. Input the password 3. Use the password toggle button to change visibility | Not Applicable | User should be able to change visibility of the password using the toggle button | Found as expected | P13 | PASS
TC 016 | (TS_001) Sign up Functionality | Checking registration button with valid credentials | Go to the webpage url https://us.shein.com/ | 1. Go to signup page 2. Fillup all the mandatory information 3. Click register | Not Applicable | User should be able to sign up in the website | Found as expected | P14 | PASS
TC 017 | (TS_001) Sign up Functionality | Checking confirmation mail sent to the registered email | Go to the webpage url https://us.shein.com/ | 1. Go to signup page 2. Fillup all the mandatory information 3. Click register 4. Check email inbox for confirmation email | Not Applicable | User should get a confirmation email in their inbox throgh which they can verify their account | Found as expected | P15 | PASS
TC 018 | (TS_001) Sign up Functionality | Checking 'Sign in with Facebook' | Go to the webpage url https://us.shein.com/ | 1. Go to signup page 2. Click sign up using facebook 3. Provide all the mandatory information | Not Applicable | User should be able to sign up | User cannot sign up, shows an error message" Error, Please try again later" | P16 | FAIL | Can't sign up with Facebook
TC 019 | (TS_001) Sign up Functionality | Checking 'Sign in with Google' | Go to the webpage url https://us.shein.com/ | 1. Go to signup page 2. Click sign up using google 3. Provide all the mandatory information | Not Applicable | User should be able to sign up | Found as expected | P17 | PASS
TC 020 | (TS_001) Sign up Functionality | Checking clicking on the link in the email verifies the account. | Go to the webpage url https://us.shein.com/ | 1. Go to signup page 2. Fill all necessary information and sign up 3. Go to email inbox and click on the confirmation email | Not Applicable | The user's account is verified and a message is displayed | The account cannot be verified and an error is displayed | P18 | FAIL | Can't verify account be email
TC 021 | (TS_001) Sign up Functionality | Checking keyboard tab button functionality | Go to the webpage url https://us.shein.com/ | 1. Go to signup page 2. Use tab button to navigate from one field to another | Not Applicable | The user should be able to use tab button to navigate from one field to another | Tab button serves no purpose in the sign up page | P19 | FAIL

## Log in
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Bug Screenshot | Comments
<< Test Scenarios
TC_LIF_001 | (TS_002) Log in Functionality | Verify logging into the website using valid credentials | Go to the webpage url https://us.shein.com/ | 1. Go to the login page 2. Input valid credentials | email: helloworld7@gmail.com pass: hello7 | User should be logged into the website | Found as expected | P2 | PASS
TC_LIF_002 | (TS_002) Log in Functionality | Verify logging into the Application using incorrect credentials (i.e. incorrect email address and Invalid Password) | Go to the webpage url https://us.shein.com/ | 1. Go to the login page 2. Input wrong credentials | email: hellodgsfsg@gmail.com pass: dzffghj | User should not be not able to log in to the website | Found as expected | P3 | PASS
TC_LIF_003 | (TS_002) Log in Functionality | Verify logging into the Application using invalid email address and valid Password | Go to the webpage url https://us.shein.com/ | 1. Go to the login page 2. Input valid email and incorrect password | email: hello123@gmail.com pass: hello7 | User is logged into the website | Found as expected | P4 | PASS
TC_LIF_004 | (TS_002) Log in Functionality | Verify logging into the Application using valid email address and invalid Password) | Go to the webpage url https://us.shein.com/ | 1. Go to the login page 2. Input incorrect email and valid password | email: helloworld7@gmail.com pass: hello7 | User is logged into the website | Found as expected | P5 | PASS
TC_LIF_005 | (TS_002) Log in Functionality | Verify logging into the Application using invalid email address | Go to the webpage url https://us.shein.com/ | 1. Go to the login page 2. Input invalid email format 3. Input password and try to log in | email: helloworld7@harry | warning message " The email you entered is invalid. Please check your email and try again" should be displayed | Found as expected |  | PASS
TC_LIF_006 | (TS_002) Log in Functionality | Verify showing proper warning messages | Go to the webpage url https://us.shein.com/ | 1. Go to login page 2. Input no credentials 3. Click on log in | Not Applicable | Warning message " Please enter an email address" should be displayed | No warning message is displayed |  | FAIL | No warning message
TC_LIF_007 | (TS_002) Log in Functionality | Verify logging into the Application without providing any credentials | Go to the webpage url https://us.shein.com/ | 1. Go to login page 2. Input no credentials 3. Click on log in | Not Applicable | User cannot log into the website | Found as expected | P6 | PASS
TC_LIF_008 | (TS_002) Log in Functionality | Verify 'Forgotten Password' link is available in the Login page and is working | Go to the webpage url https://us.shein.com/ | 1. Go to the login page 2. Input email address and click forgot password | Not Applicable | User should be taken to password restoration page | Found as expected | P7 | PASS
TC_LIF_009 | (TS_002) Log in Functionality | Verify clicking forgotten password actually leads to sending an email to the inbox for changing password | Go to the webpage url https://us.shein.com/ | 1. Go to the login page 2. Input email address and click forgot password 3. On the next page input email and click send link 4. Check email inbox for password restoration mail | Not Applicable | User should get an email and is able to successfully change the password | Found as expected | P8 | PASS
TC_LIF_010 | (TS_002) Log in Functionality | Verify location change effects on sign in | Go to the webpage url https://us.shein.com/ | 1. Go to the login page 2. Change the location 3. Input valid credentials and log in | email: helloworld7@gmail.com pass: hello7 | User should be logged into the website | User is not able to log in to the website but instead navigated to the signup page | P9 | FAIL | Location change
TC_LIF_011 | (TS_002) Log in Functionality | Verify the text into the Password field is toggled to hide its visibility | Go to the webpage url https://us.shein.com/ | 1. Go to the login page 2. Input valid credentials 3. Change the visibility of the password using the toggle button inside the password field | Not Applicable | User should be able to toggle the visibility of the password | Found as expected | P10 | PASS
TC_LIF_012 | (TS_002) Log in Functionality | Verify the copying of the text entered into the Password field | Go to the webpage url https://us.shein.com/ | 1. Go to the login page 2. Input valid credentials 3. Right click and click copy on the password field | Not Applicable | User should not be able to copy the value of the password field | Found as expected | P11 | PASS
TC_LIF_013 | (TS_002) Log in Functionality | Verify Logging into the Application after changing the password | Go to the webpage url https://us.shein.com/ | 1. Go to the login page and click forget password 2. Change the password from the link given in email 3. Login with the new credentials | Not Applicable | User should be able to log in to the website | Found as expected | P12 | PASS
TC_LIF_014 | (TS_002) Log in Functionality | Verify Logging into the Application, closing the Browser without loggingout and opening the application in the Browser again | Go to the webpage url https://us.shein.com/ | 1. Go to the login page 2. Input valid credentials to login 3. Close the brwser without logging out 4. Navigate to the page once again | Not Applicable | User should be still logged in to the website | Found as expected | P13 | PASS
TC_LIF_015 | (TS_002) Log in Functionality | Verify the UI of the Login page | Go to the webpage url https://us.shein.com/ | 1. Go to the login page 2. Checdk the page title, design etc of the webpage | Not Applicable | Webpage should be similar to the SRS document | Found as expected | P14 | PASS
TC_LIF_016 | (TS_002) Log in Functionality | Verify the Login page functionality in all the supported environments and browsers | Go to the webpage url https://us.shein.com/ | 1. Go to the login page 2. Input valid credentials to login | Not Applicable | User should be able to log in from all the supported environments and browsers | Found as expected | P15 | PASS

## Logout
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Bug Screenshot | Comments
<< Test Scenarios
TC 001 | (TS_003) Logout Functionality | Verify Logging out by selecting Logout option from 'My Account' dropmenu | 1. Open the Application URL 2. User is logged in | 1. Click on 'My Profile' Dropmenu 2. Select 'Logout' option (Verify ER-1) | Not Applicable | User should be taken to the 'Account Logout' page and User should see Login option inplace of Logout under the 'My Account' dropmenu | User is taken to the 'Account Logout' page and User should see Login option inplace of Logout under the 'My Account' dropmenu | P1 | PASS
TC 002 | (TS_003) Logout Functionality | Verify the Application session status, after logging and closing the Browser without logging out | 1. Open the Application URL 2. User is logged in | 1. Close the Browser without Logging out 2. Open the Browser and navigate the application | Not Applicable | 1. Application should not get logged out 2.The user loggedin session need to be mainitained | 1. Application is not logged out 2. The user loggedin session is mainitained | P3 | PASS
TC 003 | (TS_003) Logout Functionality | Verify logging out and browsing back | 1. Open the Application URL 2. User is logged in | 1. Click on 'My Profile' icon Dropmenu 2. Select 'Logout' option 3. Click on Browser back button | Not Applicable | 1. User should not get logged in | 1. User is not getting logged in | P1 | PASS
TC_LG_005 | (TS_003) Logout Functionality | Verify Logout option is not displayed under 'My Account' menu before logging in | 1. Open the Application URL | 1. Click on 'My Profile' icon Dropmenu | Not Applicable | 1. Logout option should not be displayed under 'My Account' dropmenu | 1. Logout option is not displayed under 'My Account' dropmenu | P3 | PASS
TC_LG_007 | (TS_003) Logout Functionality | Verify logout will be done from all places when user is logged in from different devices and logs out from one of them | 1. Open the Application URL 2. User is logged in Chrome Browser of your laptop 3. User is logged in with the same acccount of in Chrome browser | 1. Click on 'My Account' Dropmenu in Firefox Browser 2. Select 'Logout' option 3. Perform any operation which requires the user to log, like going to the my account page | Not Applicable | 1. User be logged out in the other device too, instead of getting navigated to the my account page | 1. User is not getting logged out | P3 | FAIL | User still logged in | User not logged out
TC_LG_008 | (TS_003) Logout Functionality | Verify logging out and loggin in immediately after logout | 1. Open the Application URL 2. User is logged in | 1. Click on 'My Profile' icon Dropmenu 2. Select 'Logout' option 3. Login immediately again with same or different account | Not Applicable | 1. The account should get logged in | 1. The account is getting logged in | P3 | PASS
TC_LG_009 | (TS_003) Logout Functionality | Verify 'Account Logout' page | 1. Open the Application URL 2. User is logged in | 1. Click on 'My Profile' icon Dropmenu 2. Select 'Logout' option 3. Check the Page Heading, Page Title, Page URL and Breadcrumb of the displayed 'Account Logout' page | Not Applicable | 1. Proper Page Heading, Page Title, Page URL and Breadcrumb are displayed for 'Account Logout' page which also acts as a login page | 1. Proper Page Heading, Page Title, Page URL and Breadcrumb is displayed for 'Account Logout' page | P3 | PASS
TC_LG_010 | (TS_003) Logout Functionality | Verify the UI of the Logout option and the 'Account Logout' page | 1. Open the Application URL 2. User is logged in | 1. Click on 'My Profile' icon Dropmenu 2. Select 'Logout' option | Not Applicable | 1. Proper UI adhering to the UI checklist should be displayed for Logout option | 1. Proper UI adhering to the UI checklist is displayed for Logout option | P3 | PASS
TC_LG_011 | (TS_003) Logout Functionality | Verify the Logout functionality in all the supported environments(browsers) | 1. Open the Application URL 2. User is logged in | 1. Click on 'My Profile' icon Dropmenu 2. Select 'Logout' option 3.Repeat it in different environments with different browsers | Not Applicable | Logout functionality should work correctly in all the supported environments and browsers | 1. Logout functionality is working correctly in all the supported environments and browsers | P3 | PASS

## Home Page
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_HP_001 | (TS_004) Home Page Functionality | Verify the UI of the Homepage is consistent | Go to the webpage url https://us.shein.com/ | 1.Go to the webpage url https://us.shein.com 2.Check each section for errors | Not Applicable | There should be no Ui errors | Found as expected | P3 | PASS
TC_HP_002 | (TS_004) Home Page Functionality | Verify if there are any spelling errors or grammatical errors | Go to the webpage url https://us.shein.com/ | 1.Go to the webpage url https://us.shein.com 2.Check each section for errors | Not Applicable | There should be no spelling or grammatical errors | Found as expected | P3 | PASS
TC_HP_003 | (TS_004) Home Page Functionality | Verify navigating to Home Page from 'Shopping Cart' page | Go to the webpage url https://us.shein.com/ | 1. Add some products to the cart 2. Go to the "Shopping cart" webpage 3. Navigate to the homepage | Not Applicable | User should be taken to Home page | Found as expected | P3 | PASS
TC_HP_004 | (TS_004) Home Page Functionality | Verify navigating to Home page from any page of the Website using Logo | Go to the webpage url https://us.shein.com/ | Go to the webpage and navigate to any page of the Website | Not Applicable | User should be taken to Home page | Found as expected | P3 | PASS
TC_HP_005 | (TS_004) Home Page Functionality | Verify navigating to Home page from any Category Page which don't have any products | Go to the webpage url https://us.shein.com/ | 1.Go to a product section with no available produts 2.Nabigate to the homepage using the logo link on the top corner | Not Applicable | User should be taken to Home page | Found as expected | P3 | PASS
TC_HP_006 | (TS_004) Home Page Functionality | Verify Hero Images and its slider options in the Home page | Go to the webpage url https://us.shein.com/ | 1. Check the Hero Images and slider options on the displayed Home page | Not Applicable | 1. Correct Hero Images should be displayed. 2. Hero Images should automatically slide 3. Manually user should be able to slide the Hero Images using < and > options | Found as expected | P3 | PASS
TC_HP_007 | (TS_004) Home Page Functionality | Verify the featured products should be displayed working properly | Go to the webpage url https://us.shein.com/ | 1.Check the Featured products in the displayed Home page 2. Click on each of them to go to their respective webpages | Not Applicable | 1. Featured products should be displayed correctly 2. The links of the featured products should take to the corrrect webpages | Found as expected | P3 | PASS
TC_HP_008 | (TS_004) Home Page Functionality | Verify the featured sections should be displayed working properly | Go to the webpage url https://us.shein.com/ | 1.Check the Featured section in the displayed Home page 2. Click on each of them to go to their respective webpages | Not Applicable | 1. Featured sections should be displayed correctly 2. The links of the featured products should take to the corrrect webpages | Found as expected | P3 | PASS
TC_HP_09 | (TS_004) Home Page Functionality | Verify the 'Home' page functionality in all the supported environments and browsers | Go to the webpage url https://us.shein.com/ in any browser | 1. Check the 'Home' page functionality in all the supported environments and browsers | Not Applicable | Home' page functionality should work correctly in all the supported environments and browsers | Found as expected | P3 | PASS
TC_HP_010 | (TS_004) Home Page Functionality | Verify if all the footer links are woking correctly | Go to the webpage url https://us.shein.com/ | 1. Go to the footer section of the website in the Home Page 2. Click on each of the footer links | Not Applicable | The footer links should navigate to their appropriate webpages | Found as expected | P4 | PASS
TC_HP_011 | (TS_004) Home Page Functionality | Verify the social media icons working correctly | Go to the webpage url https://us.shein.com/ | 1. Go to the footer section of the website in the Home Page 2. Click on each of the social media icons | Not Applicable | The social media icons should take us to their respective websites. | Found as expected | P5 | PASS
TC_HP_012 | (TS_004) Home Page Functionality | Verify the hover effect on the products in the home page | Go to the webpage url https://us.shein.com/ | Hover on cursor over the items displayed in the home page | Not Applicable | Multiple images should be shown along with an "Add to Cart" option appearing in the bottom part of the images | Found as expected | P6 | PASS

## Search
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Bug Screenshot | Comments
<< Test Scenarios
TC_SF_001 | (TS_005) Search Functionality | Verify searching with an existing Product Name | Go to the webpage url https://us.shein.com/ | 1. Enter any existing product name into the 'Search' text box field 2. Click on the button having search icon | Product Name: Manfinity Homme | 1. Searched product should be displayed in the search results | 1. Searched product is displayed in the search results | P1 | PASS
TC_SF_002 | (TS_005) Search Functionality | Verify searching with a non existing Product Name | Go to the webpage url https://us.shein.com/ | 1. Enter non existing product name into the 'Search' text box field 2. Click on the button having search icon | Product Name: Iphone 16 | 1. 'There is no product that matches the search criteria' should be displayed in the Search Results page | Other irrelevant products are displayed | P2 | FAIL | Irrelevant products are shown
TC_SF_003 | (TS_005) Search Functionality | Verify searching without providing any Product Name | Go to the webpage url https://us.shein.com/ | 1. Don't enter anything into the 'Search' text box field 2. Click on the button having search icon | Not Applicable | There is no product that matches the search criteria' should be displayed in the Search Results page | Other irrelevant products are displayed | P2 | FAIL | Random products are shown
TC_SF_004 | (TS_005) Search Functionality | Verifty searching for a product after login to the Application | 1.Go to the webpage url https://us.shein.com/ 2. Login to the Application | 1. Enter any existing product name into the 'Search' text box field 2. Click on the button having search icon | Product Name: Manfinity Homme | Searched product should be displayed in the search results | Searched product is displayed in the search results | P1 | PASS
TC_SF_005 | (TS_005) Search Functionality | Verify searching by providing a search criteria which results in mulitple products | Go to the webpage url https://us.shein.com/ | 1. Enter the search criteria in the 'Search' text box field which can result in mutliple products 2. Click on the button having search icon | Product Name: Manfinity | More than one products should be displayed in the search results page | More than one products are displayed in the search results page | P2 | PASS
TC_SF_006 | (TS_005) Search Functionality | Verify all the fields in the Search functionality and Search page have placeholders | Go to the webpage url https://us.shein.com/ | 1. Don't enter anything into the 'Search' text box field 2. Click on the button having search icon | Not Applicable | 1. Proper placeholder text is displayed in search text box field | Found as expected | P3 | PASS
TC_SF_007 | (TS_005) Search Functionality | Verify searching using 'Search Criteria' field | Go to the webpage url https://us.shein.com/ | 1. Don't enter anything into the 'Search' text box field 2. Click on the button having search icon 3. Enter any existing product name into the 'Search Criteria' text box field 4. Click on 'Search' button | Not Applicable | 1. Searched product should be displayed in the search results | 1. Searched product is displayed in the search results | P2 | PASS
TC_SF_008 | (TS_005) Search Functionality | Verify Search using the text from the product description | Go to the webpage url https://us.shein.com/ | 1. Enter any text from the Product Description into the 'Search Criteria' text box field 2. Click on 'Search' button | High Stretch | 1. Product having the given text in its description should be displayed in the search results | 1. Product having the given text in its description is displayed in the search results | P3 | PASS
TC_SF_009 | (TS_005) Search Functionality | Verify Search by selecting the category of product | Go to the webpage url https://us.shein.com/ | 1. Write the product name in the search box 2. Select an option from the recommednded search reselts | Manfinity | 1. Product should be successfully displayed in the search results. 2. The product catagory should be relevant | Product is successfully displayed in the correct catagory in search results. | P3 | PASS
TC_SF_012 | (TS_005) Search Functionality | Verify multiple Products UI display in the search results | Go to the webpage url https://us.shein.com/ | 1. Enter the search criteria in the 'Search' text box field which can result in mutliple products 2. Click on the button having search icon 3. View the prodcts and their add to cart options | Search Criteria: Manfinity | 1. More than one products should be displayed in the search results page 2. Multiple product should be displayed without any problems | Working as mentioned in the Actual results | P3 | PASS
TC_SF_014 | (TS_005) Search Functionality | Verify User is able to sort the Products displayed in the Search Results | Go to the webpage url https://us.shein.com/ | 1. Enter the search criteria in the 'Search' text box field 2. Click on the search icon. 3. Select several options from the 'Sort By' dropdown | Product Name: Manfinity | 1. More than one product should be displayed in the search results page 2. Products are sorted according to the options selected in the 'Sort By' dropdown field | 1. More than one product are displayed in the search results page 2. Products are sorted according to the options selected in the 'Sort By' dropdown field | P3 | PASS
TC_SF_016 | (TS_005) Search Functionality | Verify 'Search' textbox field and the button having search icon are displayed on all the page of the website | Go to the webpage url https://us.shein.com/ | 1. Navigate to all the pages of the website | Not Applicable | 1. Search box field and the button with 'Search' icon should be displayed on all the page of the website | Working as mentioned in the Actual results | P3 | PASS
TC_SF_018 | (TS_005) Search Functionality | Verify Breadcrumb of the 'Search' page | Go to the webpage url https://us.shein.com/ | 1. Enter any existing product name into the 'Search' text box field 2. Click on the button having search icon 3. Check whether the Breadcrumb option | Product Name: iMac | Breakcrumb option should be working correctly | 1. Breakcrumb option is working correctly | P3 | PASS
TC_SF_019 | (TS_005) Search Functionality | Verify we can use all the options of Search functionality using the Keyboard keys | Go to the webpage url https://us.shein.com/ | 1. Press Tab and Enter keys to perform Search operation and select several options in the Search page | Not Applicable | 1. User should be able to perform Search operation and select several options in the Search page using the Keyboard keys Tab and Enter | The function of tab key cannot be used in the searchbox | P3 | FAIL
TC_SF_020 | (TS_005) Search Functionality | Verify Page Heading, Page URL and Page Title of the 'Search' page | Go to the webpage url https://us.shein.com/ | 1. Enter any existing product name into the 'Search' text box field 2. Click on the button having search icon 3. Check the Page Heading, Page URL and Page Title of the 'Search' page | Not Applicable | A proper Page Heading, Page URL and Page Title should be displayed for 'Search' page | A proper Page Heading, Page URL and Page Title are displayed for 'Search' page | P3 | PASS
TC_SF_021 | (TS_005) Search Functionality | Verify the UI of Search functionality and Search page options | Go to the webpage url https://us.shein.com/ | 1. Enter any existing product name into the 'Search' text box field 2. Click on the button having search icon | Not Applicable | Proper UI without any errors should be displayed | Working as mentioned in the Actual results | P3 | PASS
TC_SF_022 | (TS_005) Search Functionality | Verify the Search functionality in all the supported environments and browsers | Go to the webpage url https://us.shein.com/ | 1. Enter any existing product name into the 'Search' text box field 2. Click on the button having search icon | Not Applicable | 1. Search functionality should work correctly in all the supported environments and browsers | Search functionality is working correctly in all the supported environments and browsers | P3 | PASS
TC_SF_023 | (TS_005) Search Functionality | Verify proper search history is displayed | Go to the webpage url https://us.shein.com/ | 1. Enter any existing product name into the 'Search' text box field 2. Repeat the process several times 3. Check the search history below the search bar | Not Applicable | The search keywords should be properly displayed | Working as mentioned in the Actual results | P4 | PASS
TC_SF_024 | (TS_005) Search Functionality | Verify the Search history can be deleted | Go to the webpage url https://us.shein.com/ | 1. Enter any existing product name into the 'Search' text box field 2. Repeat the process several times. 3. Click on the delete icon to erase the search history | Not Applicable | The search keywords should be deleted | Working as mentioned in the Actual results | P5 | PASS

## Forgot Password
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Bug Screenshot | Comments
<< Test Scenarios
TC_FP_001 | (TS_006) Forgot Passsword Functionality | Verify User is able to reset the password | 1. Open the WebsiteURL https://us.shein.com/ and navigate to Login Page 2. An existing Account is required | 1. Click on 'Forgotten Password' link from Login page 2. Enter the email address of an existing account for which you have forgot the password 3. Check the registered email address for which the password got reset 4. Click on the link for resseting the password from the received email body 5. Enter new password into the 'Password' and 'Confirm' fields and click continue 6. Login with the new password | Not Applicable | 1. User should be taken to 'Forgotten Password' page 2. Success message with text - 'An email with a confirmation link has been sent your email address.' should be displayed 3. Verify that an email is received from which user should be taken 'Reset your Password' page 4. Success message should be displayed 5. User should be able to login with the new password | Working as expected | P1 | PASS
TC_FP_002 | (TS_006) Forgot Passsword Functionality | Verify an email is sent with the proper details on resetting the password | 1. Open the Website URL https://us.shein.com/ and navigate to Login Page 2. An existing Account is required | 1. Click on 'Forgotten Password' link from Login page 2. Enter the email address of an existing account for which you have forgotten the password 3. Click on 'Continue' button 4. Check the registered email address for which the password got reset | Not Applicable | 1. An email should be received by the registered email address with the details of resetting the password. 2. Email should contain proper Subject, Body, from address and the link for resetting the password | Working as expected | P2 | PASS
TC_FP_003 | (TS_006) Forgot Passsword Functionality | Verify logging into the Application with the old password after resetting it | 1. An existing Account is required and we have reset the password 2. Open the website URL and navigate to Login Page | 1. Enter registered email address into the 'E-Mail address' field 2. Enter old password into the 'Password' field 3. Click on 'Login' button | Not Applicable | User should not be able to login with old password | Working as expected | P2 | PASS
TC_FP_004 | (TS_006) Forgot Passsword Functionality | Verify logging into the Application with the old password when you have initiated the resetting password process and have not reset the password | 1. Open the Application URL and navigate to Login Page 1. An existing Account is required | 1. Click on 'Forgotten Password' link from Login page and enter the email address 2. Click on 'Continue' button 3. Enter registered email address and old password 4. Click on 'Login' button | Not Applicable | User should be able to login | Working as expected | P2 | PASS
TC_FP_005 | (TS_006) Forgot Passsword Functionality | Verify resetting the password for a non-registered account | 1. Open the Application URL and navigate to Login Page | 1.Click on 'Forgotten Password' link from Login page 2. Enter an email address for which the Account doesn't exist in the application 3. Click on 'Continue' button | Not Applicable | User is taken to the sign up page | Working as expected | P2 | PASS
TC_FP_006 | (TS_006) Forgot Passsword Functionality | Verify how many times the User is able to reset the password using the reset link sent over email | 1. Open the Application URL and navigate to Login Page | 1. Click on 'Forgotten Password' link from Login page 2. Enter the email address of an existing account 3. Check the registered email address for which the password got reset 4. Click on the link for resseting the password from the received email body 5. Enter new password into the 'Password' and 'Confirm' fields 6. Repeat steps 4, 5 and 6 again. | Not Applicable | User should be allowed to use the link sent in the email for resetting the password only once | User can use the reset option in the email only once, as expected | P2 | PASS
TC_FP_007 | (TS_006) Forgot Passsword Functionality | Verify the User has given the same password into the 'Password' and 'Confirm' fields of the 'Reset your Password' page | 1. Open the Application URL and navigate to Login Page 2. An existing Account is required | 1. Go to the password reset page 2.Enter a password and re-enter it on the confirm field | Not Applicable | 1. A field level warning message with text - 'Password and password confirmation do not match!' should be displayed under 'confirm' field if password is different | Working as expected | P2 | PASS
TC_FP_008 | (TS_006) Forgot Passsword Functionality | Verify the password can be reset using phone number too | 1. Open the Application URL and navigate to Login Page 2. An existing Account is required | 1.Click on 'Forgotten Password' link from Login page 2.Click on reset password through phone number 3. Enter phone number and click confirm | Not Applicable | A text message with the link to reset password should be sent to the mobile number | Not working since only Canadian and US number can be input | P2 | Not Tested
TC_FP_009 | (TS_006) Forgot Passsword Functionality | Verify resetting the password without giving the new password in the 'Password' and 'Confirm' fields of 'Reset your Password' page | 1. An existing Account is required, we have reset the password for this account and a reset password email is sent to the registered email address | 1. Click on the reset password link available in the email 2. Don't enter any password into the 'Password' and 'Confirm' fields of the 'Reset your Password' page 3. Click on 'Continue' button | Not Applicable | Field level warning message with text - 'Password must be atleast 8 characters' should be displayed for 'Password' field | Working as expected | P3 | PASS
TC_FP_010 | (TS_006) Forgot Passsword Functionality | Verify clicking 'Back' button on the 'Reset your Password' page | 1. An existing Account is required, we have reset the password for this account and a reset password email is sent to the registered email address | 1. Click on the reset password link available in the email 2. Click on 'Back' button on the 'Reset your Password' page (Verify ER-1) | Not Applicable | 1. User should be navigated to 'Login' page | Working as expected | P3 | PASS
TC_FP_011 | (TS_006) Forgot Passsword Functionality | Verify the reset password link works for a set amount of time | 1. An existing Account is required, we have reset the password for this account and a reset password email is sent to the registered email address | 1. Click on the reset password link available in the email 2. Put in the passwords and click confirm after a set amount of time ( 2 hours) | Not Applicable | The link doesnot work anymore | Working as expected | P2 | PASS
TC_FP_012 | (TS_006) Forgot Passsword Functionality | Verify the User Interface of the 'Reset your Password' page | 1. An existing Account is required, we have reset the password for this account and a reset password email is sent to the registered email address | 1. Click on the reset password link available in the email 2. Check the UI | Not Applicable | A proper working UI should be displayed on the 'Reset your Password' page | Working as expected | P3 | PASS
TC_FP_013 | (TS_006) Forgot Passsword Functionality | Verify Page Heading, Page URL and Page Title of the 'Reset your Password' page | An existing Account is required, we have reset the password for this account and a reset password email is sent to the registered email address | 1. Click on the reset password link available in the email 2. Check the Page Heading, Page URL and Page Title | Not Applicable | 1. A proper Page Heading, Page URL and Page Title should be displayed for 'Reset your Password' page | Working as expected | P3 | PASS
TC_FP_014 | (TS_006) Forgot Passsword Functionality | Verify resseting the Password without providing the registered email address | 1. Open the Application URL and navigate to Login Page | 1. Click on 'Forgotten Password' link from Login page 2. Don't enter anything into the 'E-Mail Address' field | Not Applicable | The user is will not be able to navigate to the next page without entering the necessary information | Working as expected | P3 | PASS
TC_FP_015 | (TS_006) Forgot Passsword Functionality | Verify Placehold text is displayed in the 'E-Mail Address' field of 'Forgotten Password' page | 1. Open the Application URL and navigate to Login Page | 1. Click on 'Forgotten Password' link from Login page 2. Check Placeholder text for 'E-Mail' Address field | Not Applicable | 1. Proper Placeholder text should be displayed inside the 'E-Mail Address' fields of the 'Forgotten Password' page | No placeholder is seen | P3 | FAIL | No placeholder
TC_FP_016 | (TS_006) Forgot Passsword Functionality | Verify entering invalid format email address into the 'E-Mail Address' field of 'Forgotten Password' page | 1. Open the Application URL and navigate to Login Page | 1. Click on 'Forgotten Password' link from Login page 2. Enter any invalid formatted email address into the 'E-Mail Address' field | 1.dhsf 2.ok@hello | 1. Field level warning message informing the User to provide a valid formatted email address should be displayed | 1. Field level warning message informing the User to provide a valid formatted email address is displayed | P3 | PASS
TC_FP_017 | (TS_006) Forgot Passsword Functionality | Verify Back button on the 'Forgotten Password' page | 1. Open the Application URL and navigate to Login Page | 1. Click on 'Forgotten Password' link from Login page 2. Click on 'Back' button | Not Applicable | 1. User should be taken to 'Login' page | 1. User is taken to 'Login' page | P3 | PASS
TC_FP_018 | (TS_006) Forgot Passsword Functionality | Verify Breadcrumb of the 'Forgotten Password' page | 1. Open the Application URL and navigate to Login Page | 1. Click on 'Forgotten Password' link from Login page 2. Check the working of Breadcrumb | Not Applicable | 1. A proper working Breadcrumb should be displayed on the 'Forgotten Password' page | 1. A proper working Breadcrumb is not displayed on the 'Forgotten Password' page | P3 | FAIL | No breadcrumb
TC_FP_019 | (TS_006) Forgot Passsword Functionality | Verify the email address provided in the 'E-Mail Address' field of 'Login' page, need to be carry forwarded to the 'Forgotten Password' page | 1. Open the Application URL and navigate to Login Page | 1. Enter email address into the 'E-Mail Address' field of the Login page 2. Click on 'Forgotten Password' link | Not Applicable | 1. User should be taken to 'Forgotten Password' page and email address given in the Login page should be displayed in this page by default | Working as expected | P3 | PASS
TC_FP_020 | (TS_006) Forgot Passsword Functionality | Verify the UI of the 'Forgotten Password' page | 1. Open the Application URL and navigate to Login Page | 1. Click on 'Forgotten Password' link from Login page 2. Check the UI of the Page | Not Applicable | 1. Proper UI adhering to the UI checklist should be displayed for 'Forgotten Password' page | 1. Proper UI adhering to the UI checklist is displayed for 'Forgotten Password' page | P3 | PASS
TC_FP_021 | (TS_006) Forgot Passsword Functionality | Verify the Password entered into the 'Password' and 'Confirm' fields of 'Reset your Password' page is toggled to hide its visibility | An existing Account is required, we have reset the password for this account and a reset password email is sent to the registered email address | 1. Click on the reset password link available in the email 2. Enter any text into 'Password' and 'Confirm' fields on the 'Reset your Password' page | Not Applicable | Text entered into the 'Password' and 'Confirmed' fields should be toggled to hide its visibility | No toggling option in the password reset page | P2 | FAIL | No toggling option
TC_FP_022 | (TS_006) Forgot Passsword Functionality | Verify the Password Reset functionality in all the supported environments and browsers | 1. Open the Application URL and navigate to Login Page | 1. Click on 'Forgotten Password' link from Login page | Not Applicable | 1. Reset Password functionality should work correctly in all the supported environments and browsers | Working as expected | P2 | PASS

## My Account
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Bug Screenshot | Comments
<< Test Scenarios
TC_MA_001 | (TS_007) My Account Functionality | Verify navigating to 'My Account' page after login | Open the Website URL https://us.shein.com/ and login | 1. Login using email and password 2. Click on my account icon | Not Applicable | 1. User should be taken to 'My Account' page | Working as mentioned in the Expected Result section | P3 | PASS
TC_MA_002 | (TS_007) My Account Functionality | Verify if information can be changed in "My account page" | Open the Website URL https://us.shein.com/ and login | 1. Login using email and password 2. Click on my account icon 3. Click on "Nickname" field and edit 4.Click Save | Not Applicable | The new information should be saved | Working as mentioned in the Expected Result section | P2 | PASS
TC_MA_003 | (TS_007) My Account Functionality | Verify navigating to 'My Account' page using 'My Account' option | Open the Website URL https://us.shein.com/ and login | 1. Click on 'My Account' dropmenu 2. Click on 'My Account' option (Verify ER-1) | Not Applicable | 1. User should be taken to 'My Account' page | Working as mentioned in the Expected Result section | P3 | PASS
TC_MA_004 | (TS_007) My Account Functionality | Verify Success pop up after information change | Open the Website URL https://us.shein.com/ and login | 1. Login and go to "My account" page 2. change a certain information and save 3. Check for a green popup would appear with the text "Success" | Not Applicable | A green popup would appear with the text "Update Success" | Working as mentioned in the Expected Result section | P2 | PASS
TC_MA_005 | (TS_007) My Account Functionality | Verify selecting preferences in "My account" | Open the Website URL https://us.shein.com/ and login | 1. Login and go to "My account" page 2. Select one or more preferences from each of the fields 3. Click Save | Not Applicable | A green popup would appear with the text "Update Success" | Working as mentioned in the Expected Result section | P2 | PASS
TC_MA_006 | (TS_007) My Account Functionality | Verify Breadcrump in 'My Account' page | Open the Website URL https://us.shein.com/ and login | 1. Click on 'My Account' dropmenu 2. Click on 'My Account' option 3. Verify the Breadcrumb in the displayed 'My Account' page | Not Applicable | Breadcrumb should be displayed in the 'My Account' page and is working properly | Working as mentioned in the Expected Result section | P3 | PASS
TC_MA_007 | (TS_007) My Account Functionality | Verify Page URL, Page Heading and Page Title of the 'My Account' page | Open the Website URL https://us.shein.com/ and login | 1. Click on 'My Account' dropmenu 2. Click on 'My Account' option 3. Check the Page URL, Page Title and Page Heading that is displayed in the 'My Account' page | Not Applicable | 1. Correct Page URL, Page Title and Page Heading should be displayed | Working as mentioned in the Expected Result section | P3 | PASS
TC_MA_008 | (TS_007) My Account Functionality | Verify the UI of 'My Account' page functionality | Open the Website URL https://us.shein.com/ and login | 1. Check the UI of the functionality related to 'My Account' page | Not Applicable | 1. Proper UI adhering to the UI checklist should be displayed for the 'My Account' page functionality | Working as mentioned in the Expected Result section | P3 | PASS
TC_MA_009 | (TS_007) My Account Functionality | Verify the 'My Account' page functionality in all the supported environments and browsers | Open the Website URL https://us.shein.com/ and login in any supported browser | 1. Check the 'My Account' page functionality in all the supported environments and browsers | Not Applicable | 1. 'My Account' page functionality should work correctly in all the supported environments and browsers | Working as mentioned in the Expected Result section | P3 | PASS
TC_MA_010 | (TS_007) My Account Functionality | Check each of the links inside "My account" Section | Open the Website URL https://us.shein.com/ and login in any supported browser | 1. Login to the account 2. Go to My accounts section 3. Check each of the links inside the My Accounts | Not Applicable | Links should properly open and navigate to where they are supposed to | Working as mentioned in the Expected Result section | P4 | PASS
TC_MA_011 | (TS_007) My Account Functionality | Verify the address book section inside the My Account | Open the Website URL https://us.shein.com/ and login in any supported browser | 1. Login to the account 2. Go to My accounts section 3. Navigate to Address book 4. Enter an address and save it | Not Applicable | The addess should be displayed in the address book section | Working as mentioned in the Expected Result section | P2 | PASS
TC_MA_012 | (TS_007) My Account Functionality | Verify the text fields in address book to have proper place holders | Open the Website URL https://us.shein.com/ and login in any supported browser | 1. Login to the account 2. Go to My accounts section 3. Navigate to Address book 4. Check to see placeholders in text fields | Not Applicable | Text fields must have proper place holders | Working as mentioned in the Expected Result section | P2 | PASS
TC_MA_013 | (TS_007) My Account Functionality | Verify the download your information funtionality | Open the Website URL https://us.shein.com/ and login | 1. Go to my accounts section 2. Navigate to manage my account 3. Click download your information | Not Applicable | The information should be downloaded properly | Working as mentioned in the Expected Result section |  | PASS
TC_MA_014 | (TS_007) My Account Functionality | Verify the available copies in "Download your information" should be none if no copies were requested previously | Open the Website URL https://us.shein.com/ and login | 1. Go to my accounts section 2. Navigate to manage my account 3. Click download your information 4. Click on available copies and check | Not Applicable | There should be no available copies if no copies were previously requested | Working as mentioned in the Expected Result section |  | PASS
TC_MA_015 | (TS_007) My Account Functionality | Verify the radio button in the request copy section of "Download your Information" | Open the Website URL https://us.shein.com/ and login | 1. Go to my accounts section 2. Navigate to manage my account 3. Click download your information and then request copy 4. Select the available radio button | Not Applicable | The radio button should be working properly in the request copy section | Working as mentioned in the Expected Result section |  | PASS
TC_MA_016 | (TS_007) My Account Functionality | Verify accessing the delete account option from manage my account | Open the Website URL https://us.shein.com/ and login | 1. Go to my accounts section 2. Navigate to manage my account 3. Click delete account | Not Applicable | The delete account option should be accessible from manage my account | Working as mentioned in the Expected Result section |  | PASS
TC_MA_017 | (TS_007) My Account Functionality | Verify getting an email to delete account from the website | Open the Website URL https://us.shein.com/ and login | "1. Go to my accounts section 2. Navigate to manage my account 3. Click delete account 4. Then select "Apply to delete account" to get the email 5 Check inbox in email address to check the email | Not Applicable | The user should get an email with details about deleting the account | Working as mentioned in the Expected Result section |  | PASS
TC_MA_018 | (TS_007) My Account Functionality | Verify the address book by giving blank information | Open the Website URL https://us.shein.com/ and login in any supported browser | 1. Login to the account 2. Go to My accounts section 3. Navigate to Address book 4. Click save without providing any information | Not Applicable | The text fields should display relevant errors underneath them | Working as mentioned in the Expected Result section | P2 | PASS
TC_MA_019 | (TS_007) My Account Functionality | Check the address book mandatory fields | Open the Website URL https://us.shein.com/ and login in any supported browser | 1. Login to the account 2. Go to My accounts section 3. Navigate to Address book 4. Try to save without providing a mandatory information | Not Applicable | The text fields should display relevant errors underneath them | Working as mentioned in the Expected Result section | P2 | PASS
TC_MA_020 | (TS_007) My Account Functionality | Check the "make default" checkbox in the address book | Open the Website URL https://us.shein.com/ and login in any supported browser | 1. Login to the account 2. Go to My accounts section 3. Navigate to Address book and provide necessary information 4. Mark the checkbox for "make default" | Not Applicable | The address will be made default | Working as mentioned in the Expected Result section | P2 | PASS
TC_MA_021 | (TS_007) My Account Functionality | Verify the My measurements section inside the My Account | Open the Website URL https://us.shein.com/ and login in any supported browser | 1. Login to the account 2. Go to My accounts section 3. Navigate to my measurements 4. Enter relevant information and save | Not Applicable | The measurements should be displayed in the my measurements section | Working as mentioned in the Expected Result section | P2 | PASS
TC_MA_022 | (TS_007) My Account Functionality | Verify the drop dows menus in my measurement to have proper place holders | Open the Website URL https://us.shein.com/ and login in any supported browser | 1. Login to the account 2. Go to My accounts section 3. Navigate to Address book 4. Check to see placeholders in drop down menus | Not Applicable | drop down menus must have proper place holders | Working as mentioned in the Expected Result section | P2 | PASS

## Address Book
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Bug Screenshot | Comments
<< Test Scenarios
TC_AB_001 | (TS_008) Address Book Functionality | Verify navigating to 'Address Book Entries' page from 'My Account' dropmenu | Open the Website URL https://us.shein.com/ and login | 1. Click on 'My Account' dropmenu 2. Click on 'My Account' option 3. Click on 'Address Book' link | Not Applicable | User should be taken to 'Address Book Entries' page | Working as mentioned in the Expected Result section | P3 | PASS
TC_AB_002 | (TS_008) Address Book Functionality | Verify navigating to 'Address Book Entries' page from Right Column options before logging into the Website | 1. Open the Website URL https://us.shein.com/ 2. User has not logged in | 1. Go to the website 2. Click on 'My Account' dropmenu 3. Check for the Address Book section | Provide Email and Password | 1. User should be taken to 'Login' page | Working as mentioned in the Expected Result section | P3 | PASS
TC_AB_003 | (TS_008) Address Book Functionality | Verify default address displayed in the 'Address Book Entries' page | Open the Website URL https://us.shein.com/ and login | 1. Login with an existing account 2. Navigate to Address Book section 3. Check default address | Not Applicable | Address given as default should be displayed as default address in the 'Address Book Entries' page | Working as mentioned in the Expected Result section | P3 | PASS
TC_AB_004 | (TS_008) Address Book Functionality | Verify deleting the default address in the 'Address Book Entries' page | Open the Website URL https://us.shein.com/ and login | 1. Click on 'Address Book' option 2. Click on 'Delete' button of the default address displayed in the 'Address Book Entries' page | Not Applicable | 1. Warning Message with text - 'You can not delete your default address!' should be displayed and the address should not get deleted. | The address gets deleted without any warning | P3 | FAIL | Address gets deleted
TC_AB_005 | (TS_008) Address Book Functionality | Verify updating the Address in the 'Address Book Entries' page | Open the Website URL https://us.shein.com/ and login | 1. Click on 'Address Book' option 2. Click on 'Edit' button of the an address displayed in the 'Address Book Entries' page 3. Change some information and click save | Not Applicable | The address is successfully changed and can be viewed in the address book | Working as mentioned in the Expected Result section | P1 | PASS
TC_AB_006 | (TS_008) Address Book Functionality | Verify "make default address" appers in all other addresses after deltion on the old default address | 1.Open the Website URL https://us.shein.com/ and login 2. No default address in address book | 1. Click on 'Address Book' option 2. Check if all other addresses have "make default address " option | Not Applicable | All other addresses have "make default address " option | Working as mentioned in the Expected Result section | P3 | PASS
TC_AB_007 | (TS_008) Address Book Functionality | Verify updating the Address by not putting information on the non-mandatory fields | Open the Website URL https://us.shein.com/ and login | 1. Click on 'Address Book' option 2. Click on 'Edit' button of an address in the displayed 'Address Book Entries' page 3. Clear the details from all the non-mandatory fields of the address in the displayed 'Edit Address' page 4. Click on 'Continue' button | Not Applicable | Success message with text - ' Your address has been successfully updated' should be displayed | Working as mentioned in the Expected Result section | P3 | PASS
TC_AB_008 | (TS_008) Address Book Functionality | Verify clearing all the fields in the 'Edit Address' page and updating the Address | Open the Website URL https://us.shein.com/ and login | 1. Click on 'Address Book' option 2. Click on 'Edit' button of an address in the displayed 'Address Book Entries' page 3. Clear the details from all the fields of the address in the displayed 'Edit Address' page 4. Click on 'Continue' button | Not Applicable | 1. Field level warning messages should be displayed for all the mandatory fields | Working as mentioned in the Expected Result section | P3 | PASS
TC_AB_009 | (TS_008) Address Book Functionality | Verify Back button in the 'Edit Address' page | Open the Website URL https://us.shein.com/ and login | 1. Click on 'Address Book' option 2. Click on 'Edit' button of an address in the displayed 'Address Book Entries' page 3. Update all the fields of the address in the displayed 'Edit Address' page 4. Click on 'Back' button | Not Applicable | 1. User should be taken to the 'Address Book Entries' page and the changes to the fields should be lost without getting updated. | Working as mentioned in the Expected Result section | P3 | PASS
TC_AB_010 | (TS_008) Address Book Functionality | Verify Back button in the 'Address Book Entries' page | Open the Website URL https://us.shein.com/ and login | 1. Click on 'Address Book' option from Right Column options 2. Click on 'Back' button in the displayed 'Address Book Entries' page (Verify ER-1) | Not Applicable | 1. User should be taken to 'My Account' page | Working as mentioned in the Expected Result section | P3 | PASS
TC_AB_011 | (TS_008) Address Book Functionality | Verify adding new Address by providing only the mandatory fields | Open the Website URL https://us.shein.com/ and login | 1. Click on 'Address Book' option 2. Click on 'New Address' button 3. Enter details into only mandatory fields 4. Click on 'Continue' button | Not Applicable | 1. User should be taken to 'Add Address' page | Working as mentioned in the Expected Result section | P1 | PASS
TC_AB_012 | (TS_008) Address Book Functionality | Verify selecting the newly added Address as default address | Open the Website URL https://us.shein.com/ and login | 1. Click on 'Address Book' option from Right Column options 2. Select a newly created address as a default address 3. Click save | Not Applicable | The new address should become the default address | Working as mentioned in the Expected Result section | P3 | PASS
TC_AB_013 | (TS_008) Address Book Functionality | Verify new address given for Billing Details while placing the order should get added in 'Address Book Entries' page | Open the Website URL https://us.shein.com/ and login | 1. Purchase a product and navigate to checkout. 2. Open the address book and add a new address 3. Save and close it 4. Navigate to address book 5. Check for the new address | Not Applicable | 1. Address given in the 'Checkout' Section while creating the order should be displayed in the 'Address Book Entries' page | Working as mentioned in the Expected Result section | P3 | PASS
TC_AB_014 | (TS_008) Address Book Functionality | Verify new address given for Delivery Details while placing the order should get added in 'Address Book Entries' page | Open the Website URL https://us.shein.com/ and login | 1. Purchase a product and navigate to delivery. 2. Open the address book and add a new address 3. Save and close it 4. Navigate to address book 5. Check for the new address | Not Applicable | 1. Address given in the 'Delivery Details' Section while creating the order should be displayed in the 'Address Book Entries' page | Working as mentioned in the Expected Result section | P3 | PASS
TC_AB_015 | (TS_008) Address Book Functionality | Verify the Breadcrumb, Page URL, Page Heading and Page Title of 'My Address Book' page | Open the Website URL https://us.shein.com/ and login | 1. Click on 'Address Book' option from Right Column options 2. Check Breadcrumb, Page URL, Page Heading and Page Title of 'Address Book Entries' page | Not Applicable | 1. Breadcrumb should be displayed and properly working in the 'Address Booke Entries' page. Correct Page URL, Page Heading and Page Title should also be displayed | Working as mentioned in the Expected Result section | P3 | PASS
TC_AB_016 | (TS_008) Address Book Functionality | Verify fields of the "Edit address" page | Open the Website URL https://us.shein.com/ and login | 1. Click on 'Address Book' option from Right Column options 2. Click on 'Edit' button of any address in the 'Address Book Entries' page | Not Applicable | Relevant errors or warning should be displayed | Working as mentioned in the Expected Result section | P3 | PASS
TC_AB_017 | (TS_008) Address Book Functionality | Verify the UI of Address Book functionality | Open the Website URL https://us.shein.com/ and login | 1. Check the UI of the functionality related to 'Address Book' functionality (Verify ER-1) | Not Applicable | 1. Proper UI adhering to the UI checklist should be displayed for the 'Address Book' functionality | Working as mentioned in the Expected Result section | P3 | PASS
TC_AB_018 | (TS_008) Address Book Functionality | Verify the 'Address Book' page functionality in all the supported environments and browsers | Open the Website URL https://us.shein.com/ and login | 1. Check the 'Address Book' functionality in all the supported environments and browsers | Not Applicable | 1. 'Address Book' functionality should work correctly in all the supported environments and browsers | Working as mentioned in the Expected Result section | P3 | PASS

## Wishlist
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Bug Screenshot | Comments
<< Test Scenarios
TC_WL_001 | (TS_009) Wish List Functionality | Verify adding a product to 'Wish List' page from 'Product Display' page | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Click on the add to wishlist icon 3. Navigate to the my wishlist section 4. Check the product that was wishlisted | Not Applicable | Product should be successfully displayed in the 'My Wish List' page | Working as mentioned in the Expected Result section | P1 | PASS
TC_WL_002 | (TS_009) Wish List Functionality | Verify a wishlisted product can be added to cart | Open the Website URL https://us.shein.com/ and login | 1. Add a product to the wishlist 2. Go to the My wishlist page 3. Hover over the image of the product and click Add to Cart | Not Applicable | Product should be added to Add to cart from my wishlist | Working as mentioned in the Expected Result section | P2 | PASS
TC_WL_003 | (TS_009) Wish List Functionality | Verify the filters in the my wishlist page works perfectly | Open the Website URL https://us.shein.com/ and login | 1. Add several product to the wishlist 2. Go to the My wishlist page 3. Change the conditions of the filter | Not Applicable | The filter in the Wish List page should display the right produtcs matching the criterias | Working as mentioned in the Expected Result section | P1 | PASS
TC_WL_004 | (TS_009) Wish List Functionality | Verify the sort funtionality working correctly | Open the Website URL https://us.shein.com/ and login | 1. Add several product to the wishlist 2. Go to the My wishlist page 3. Change the conditions of the sort option | Not Applicable | The products should be displayed according to the condition of the sort function | Working as mentioned in the Expected Result section | P1 | PASS
TC_WL_005 | (TS_009) Wish List Functionality | Verify adding a product to 'Wish List' page from the Product that is displayed in the 'Featured' section of 'Home' page | Open the Website URL https://us.shein.com/ and login | 1. Click on a product from the featured section of the homepage 2. Click on the add to wishlist icon on the product details page 3. check for the product in the my wishlist page | Not Applicable | Product should be successfully displayed in the 'My Wish List' page | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_006 | (TS_009) Wish List Functionality | Verify the wishlist icon counter is updated in real time when a product is wish listed | Open the Website URL https://us.shein.com/ and login | 1. Go to a product details page 2. Click on the add to wishlist icon 3. Check on the upper right corner of the page to see if the wishlist icon counter has increased | Not Applicable | The wishlist counter is updated | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_007 | (TS_009) Wish List Functionality | Verify adding a product to 'Wish List' page from the Search Results page | Open the Website URL https://us.shein.com/ and login | 1. Enter any existing Product name into the Search text box field 2. Click on the button having search icon 3. Click on 'Add to Wish List' option of a product that is dispayed in the 'Search Results' page | Not Applicable | Product should be added to the wishlist from the search results page | No option to add products from search results page | P3 | FAIL | Can't add to wishlist
TC_WL_008 | (TS_009) Wish List Functionality | Verify the products details of the items in the wishlist | Open the Website URL https://us.shein.com/ and login | 1. Go to a product details page 2. Click on the add to wishlist icon 3. Go to my wishlist page 4. Check the product details | Not Applicable | The product details should be exacly same in the my wishlist page | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_009 | (TS_009) Wish List Functionality | Verify navigating to 'My Wish List' page from the 'My Account' page | Open the Website URL https://us.shein.com/ and login | 1. Go to "My Accounts" on the webpage. 2. Navigate to "My Concern" dropdown menu. 3. Click on my wishlist link | Not Applicable | User should be able to navigate to my wishlist from his/her My account page | Working as mentioned in the Expected Result section | P2 | PASS
TC_WL_010 | (TS_009) Wish List Functionality | Verify the Breadcrumb in the 'Wish List' page | Open the Website URL https://us.shein.com/ and login | 1. Navigate to the My wishlist webpage 2. Checkout the breadcrumbs on the top left of the page | Not Applicable | Correct Breadcrumb should be displayed in the 'Wish List' page and should work correctly | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_011 | (TS_009) Wish List Functionality | Verify the Page Title, Page URL and Page Heading of 'Wish List' page | Open the Website URL https://us.shein.com/ and login | 1. Click on 'My wish list' option 2. Check the Page Title, Page URL and Page Heading of the displayed 'Wish List' page | Not Applicable | Correct Page Title, Page URL and Page Heading should be displayed | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_012 | (TS_009) Wish List Functionality | Verify the 'My Wish List' page when there are no products added | 1. Open the Website URL https://us.shein.com/ and login 2. No products are added to 'My Wish List' page | 1. Click on 'My wish list' option and check the wishlist products | Not Applicable | No products should be displayed | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_013 | (TS_009) Wish List Functionality | Verify the 'My Wish List' page when only one product is added to it | 1. Open the Website URL https://us.shein.com/ and login 2. One product is added to 'My Wish List' page | 1. Click on 'My wish list' option 2. check the wishlist products | Not Applicable | Only one product should be displayed with proper title, size and colour | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_014 | (TS_009) Wish List Functionality | Verify removing a Product from 'My Wish List' page | 1. Open the Website URL https://us.shein.com/ and login 2. Atleast one product is added to 'My Wish List' page | 1. Click on 'My wish list' option 2. check the wishlist products 3. Click on 'Remove' icon option | Not Applicable | No products should be displayed in the My wishlist page | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_015 | (TS_009) Wish List Functionality | Verify removing all products from My Wishlist | 1. Open the Website URL https://us.shein.com/ and login 2. Multiple products are added to 'My Wish List' page | 1. Click on 'My wish list' option 2. check the wishlist products 3. Click on 'Remove' icon option 4. Repeat until all products are removed | Not Applicable | No products should be displayed in the My wishlist page | Working as mentioned in the Expected Result section | P1 | PASS
TC_WL_016 | (TS_009) Wish List Functionality | Verify adding the multiple products to the 'My Wish List' page | 1. Open the Application URL and login 2. Add multiple products to 'My Wish List' page | 1. Go to the products details page of several products. 2. Add them to My wishlist | Not Applicable | My wishlish page should be able to display all the procts with proper details | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_017 | (TS_009) Wish List Functionality | Verify adding duplicate products to 'My Wish List' page | Open the Website URL https://us.shein.com/ and login | 1. Enter any existing product to wishlist. 2. Try to re-enter the same product to the wishlist | Not Applicable | User should not be able to enter the same product to the wishlist twice | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_018 | (TS_009) Wish List Functionality | Verify removing a product from wishlist and then adding it again | 1.Open the Website URL https://us.shein.com/ and login 2. Atleast one product should already be in the wishlist | 1. Remove a product from the wishlist 2. Try to re-enter the same product into the wishlist | Not Applicable | User should be able to re-enter the product after it was deleted from the wishlist | Working as mentioned in the Expected Result section | P1 | PASS
TC_WL_019 | (TS_009) Wish List Functionality | Verify the UI of 'Wish List' funtionality | Open the Website URL https://us.shein.com/ and login | 1. Check the UI of the functioanality related to 'Wish List' | Not Applicable | Proper UI adhering to the UI checklist should be displayed for the 'Wish List' functionality | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_020 | (TS_009) Wish List Functionality | Verify the 'Wish List' functionality in all the supported environments and browsers | Open the Website URL https://us.shein.com/ and login in any supported browser | 1. Check the 'Wish List' functionality in all the supported environments and browsers | Not Applicable | 'Wish List' functionality should work correctly in all the supported environments and browsers | Working as mentioned in the Expected Result section | P3 | PASS

## Add to Cart
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Bug Screenshot | Comments
<< Test Scenarios
TC_WL_001 | (TS_010) Add to cart Functionality | Verify adding a product to "Add to Cart" by clicking the add to cart icon on the product page | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Click on the add to cart icon 3. Navigate to the view cart section 4. Check the product that was added | Not Applicable | Product should be successfully displayed in the 'View Cart' page | Working as mentioned in the Expected Result section | P1 | PASS
TC_WL_002 | (TS_010) Add to cart Functionality | Checking if the "Add to Cart" button works without selecting the size | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Click on the add to cart icon without selecting the size | Not Applicable | Product should not be added to Add to cart and an error should be displayed | Working as mentioned in the Expected Result section | P2 | PASS
TC_WL_003 | (TS_010) Add to cart Functionality | Verify that the quantity of the item in the cart increments correctly when the "Add to Cart" button is clicked multiple times. | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Click on the add to cart icon 3. Repeat the same process for several other products 4. Check if the car summary shows all the products when the add to cart button is clicked | Not Applicable | The number of items in the cart should increase | Working as mentioned in the Expected Result section | P1 | PASS
TC_WL_004 | (TS_010) Add to cart Functionality | Verify that the product details (price, color, size, etc.) in the cart match the selected item on the product page. | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Click on the add to cart icon 3. Go to view cart page 4. Compare the details of the products | Not Applicable | The product details should be exactly same for both the product details page and the view cart page | Working as mentioned in the Expected Result section | P2 | PASS
TC_WL_005 | (TS_010) Add to cart Functionality | Verify if products can be deleted from the cart | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Click on the add to cart icon 3. Go to view cart page 4. Press on the delete icon | Not Applicable | The product should be deleted from the cart | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_006 | (TS_010) Add to cart Functionality | Verify the cart icon changes to reflect the number of items in cart | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Click on the add to cart icon 3. Repeat the same process for several other products 4. Check if the cart icon shows an incremented value when the add to cart botton is clicked | Not Applicable | The number of items in the cart icon should increase | Working as mentioned in the Expected Result section | P4 | PASS
TC_WL_007 | (TS_010) Add to cart Functionality | Verify that when hovering over "Add to Cart" option a summary of the items inside the cart is shown | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Click on the add to cart icon 3. Hover over the cart summary | Not Applicable | A summary of all the products inside the cart is displayrd | Working as mentioned in the Expected Result section | P5 | PASS
TC_WL_009 | (TS_010) Add to cart Functionality | Add items to the cart and proceed to the checkout. Confirm that the items added are correctly reflected in the checkout page. | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Click on the add to cart icon 3. Go to checkout option | Not Applicable | The product details in cart and checkout page should be the same | Working as mentioned in the Expected Result section | P7 | PASS
TC_WL_010 | (TS_010) Add to cart Functionality | Check if any discounts or coupons are properly added to "Add to Cart" items | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Click on the add to cart icon 3. Go to cart summary 4. Check if the discounts or coupons on the products are properly applied | Not Applicable | The discounts are properly added to the cart page | Working as mentioned in the Expected Result section | P8 | PASS

## Product Details
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Bug Screenshot | Comments
<< Test Scenarios
TC_WL_001 | (TS_011) Product Display Functionality | Verify the Thumbnails of the Product displayed in the Product Display Page | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Hover over the picture of an item | Not Applicable | The thumbnail should change the picture | Working as mentioned in the Expected Result section | P1 | PASS
TC_WL_002 | (TS_011) Product Display Functionality | Verify that Product Name, Brand and Product Code are displayed in the Product Display Page | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Check the details of the products that are shown in the products display page | Not Applicable | Proper product details should be displayed | Working as mentioned in the Expected Result section | P2 | PASS
TC_WL_003 | (TS_011) Product Display Functionality | Verify the Price of the Product with and without discounts is displayed in the Product Display Page | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Check the price tag of the products | Not Applicable | Both the original price and the discounted price should be displayed | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_004 | (TS_011) Product Display Functionality | Verify the default quanity for the Product is displayed as 1 in the Product Display Page, when there is no minimum quantity set for the Product | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Check the number of quantity of products as default | Not Applicable | The number of products as default should be 1 | Working as mentioned in the Expected Result section | P4 | PASS
TC_WL_005 | (TS_011) Product Display Functionality | Verify the description of the Product in the Product Display Page | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Check the details of the products that are shown in the products display page | Not Applicable | Correct Description of the product without any spelling or grammatical mistakes should be displayed for different types of Products. | Working as mentioned in the Expected Result section | P5 | PASS
TC_WL_006 | (TS_011) Product Display Functionality | Verify that a review of a product cannot be given without actually buying the product | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Try to give a review of a product | Not Applicable | The review of a product cannot be given without actually buying the product | Working as mentioned in the Expected Result section | P6 | PASS
TC_WL_007 | (TS_011) Product Display Functionality | Verify average rating of the product should be displayed in the reviews section | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Check the average ratings of the products that are shown in the products display page | Not Applicable | The average rating of the product should be displayed in the reviews section | Working as mentioned in the Expected Result section | P7 | PASS
TC_WL_008 | (TS_011) Product Display Functionality | Verify the name, date and other relevant details are also displayed with the review | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Check the details of a review | Not Applicable | The details of the product should be displayed in the review section | Working as mentioned in the Expected Result section | P8 | PASS
TC_WL_009 | (TS_011) Product Display Functionality | Verify adding the product to 'Wish List' from the Product Display page | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Click on the wishlist icon to add it to wishlist | Not Applicable | Product should be wishlisted | Working as mentioned in the Expected Result section | P9 | PASS
TC_WL_010 | (TS_011) Product Display Functionality | Verify adding the product to 'Add to Cart' from the Product Display page | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Click on the add to cart icon to add it to the cart | Not Applicable | Product should be added to the cart | Working as mentioned in the Expected Result section | P10 | PASS
TC_WL_011 | (TS_011) Product Display Functionality | Verify proper options for liking, tweeting, sharing the Product Display page on social platforms | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Check if sharing to social media option is available | Not Applicable | There should be several links or icons to share in the social media sites | No options to share in the soicial media | P11 | FAIL | No social media buttons
TC_WL_012 | (TS_011) Product Display Functionality | Verify that the delivery options are properly displayed in details | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Check the delivery options | Not Applicable | Proper delivery details should be displayed | Working as mentioned in the Expected Result section | P12 | PASS
TC_WL_013 | (TS_011) Product Display Functionality | Verify 'Related Products' section in Product Display page | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Check the "Customers also viewed" section | Not Applicable | The related products "Customer also viewed" section is working properly | Working as mentioned in the Expected Result section | P13 | PASS
TC_WL_014 | (TS_011) Product Display Functionality | Verify the Reward Points displayed in the Product Display page | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Check the amount of points that could be obtained by purchasing that product | Not Applicable | The reward points section should be displayed | Working as mentioned in the Expected Result section | P14 | PASS
TC_WL_015 | (TS_011) Product Display Functionality | Verify all the extra available options in the Product Display page | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Check the extral available options such as selecting size or size guide in the product display page | Not Applicable | Extra available section is should display options such as selecting size or size guide in the product display page | Working as mentioned in the Expected Result section | P15 | PASS
TC_WL_016 | (TS_011) Product Display Functionality | Verify the UI of 'Product Display' page | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Check the UI of the display product page | Not Applicable | Proper product details should be displayed | Working as mentioned in the Expected Result section | P16 | PASS
TC_WL_017 | (TS_011) Product Display Functionality | Verify the 'Product Display' page functionality in all the supported environments and browsers | Open the Website URL https://us.shein.com/ and login | Check the 'Product Display' page in all the supported environments and browsers | Not Applicable | The product display page should work in all suppoted environments and browsers | Working as mentioned in the Expected Result section | P17 | PASS

## Checkout
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Bug Screenshot | Comments
<< Test Scenarios
TC_WL_001 | (TS_012) Checkout Functionality | Verify navigating to Checkout page when there are no products added to the Shopping Cart | Open the Website URL https://us.shein.com/ and login | 1. Go to the add to cart page 2. Do not add any item to add to cart 3. Try to navagate to the checkout page | Not Applicable | User cannot navigate to the checkout page without adding anything to the shopping cart | Working as mentioned in the Expected Result section | P1 | PASS
TC_WL_002 | (TS_012) Checkout Functionality | Verify navigating to Checkout page from 'Shopping Cart' page | Open the Website URL https://us.shein.com/ and login | 1. Go to the checkout page and add atleast one product 2. Click on the textbox beside the product 3. Press checkout now button | Not Applicable | User should be able to navigate to checkout page from shopping cart page | Working as mentioned in the Expected Result section | P2 | PASS
TC_WL_003 | (TS_012) Checkout Functionality | Verify order summary is showing proper details such as price, shipping cost, discount etc | Open the Website URL https://us.shein.com/ and login | 1. Go to the checkout page and add atleast one product 2. Click on the textbox beside the product 3. Press checkout now button 4. Check the order summary | Not Applicable | User should be able to see the details of their purchase | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_004 | (TS_012) Checkout Functionality | Verify Checkout as Signed in User by using an existing address during checkout | Open the Website URL https://us.shein.com/ and login | 1. Go to the checkout page and add atleast one product 2. Click on the textbox beside the product 3. Press checkout now button 4. Select an existing address | Not Applicable | User should be able to use an existing address for shipping | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_005 | (TS_012) Checkout Functionality | Verify Checkout as Signed in User by entering new address into the mandatory fields of the Billing Details section during checkout | Open the Website URL https://us.shein.com/ and login | 1. Go to the checkout page and add atleast one product 2. Click on the textbox beside the product 3. Press checkout now button 4. Create a new address and select it | Not Applicable | User should be able to create a new shipping address and ship out in that new address | Working as mentioned in the Expected Result section | P4 | PASS
TC_WL_006 | (TS_012) Checkout Functionality | Verify the default address is displayed as the shipping address when no other address is selected manually | Open the Website URL https://us.shein.com/ and login | 1. Go to the checkout page and add atleast one product 2. Click on the textbox beside the product 3. Press checkout now button 4. Check the address | Not Applicable | The address should be the default address that is saved in the my account section of the webpage | Working as mentioned in the Expected Result section | P5 | PASS
TC_WL_007 | (TS_012) Checkout Functionality | Verify the radio buttons to choose the shipping options are working properly | Open the Website URL https://us.shein.com/ and login | 1. Go to the checkout page 2. Select each radio button and try to proceed | Not Applicable | The radio buttons should be working properly | Working as mentioned in the Expected Result section | P6 | PASS
TC_WL_008 | (TS_012) Checkout Functionality | Verify the order summary changes each time the shipping options are changed | Open the Website URL https://us.shein.com/ and login | 1. Go to the checkout page 2. Select each radio button 3. Each time check the order summary to notice any changes | Not Applicable | The order summary should change to reflect the changes made in the shipping options | Working as mentioned in the Expected Result section | P7 | PASS
TC_WL_009 | (TS_012) Checkout Functionality | Verify each of the options in the payment methods are working properly | Open the Website URL https://us.shein.com/ and login | 1. Go to the checkout page 2. Select each of the payment options 3. Proceed to payment | Not Applicable | Each of the option in the payment method should be working properly | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_010 | (TS_012) Checkout Functionality | Verify reward points are provided with each purchase | Open the Website URL https://us.shein.com/ and login | 1. Go to the checkout page 2. Check to see how much reward points are awarded with that purchase under the order summary section | Not Applicable | The user should be awaded rewards points after each purchase | Working as mentioned in the Expected Result section | P4 | PASS
TC_WL_011 | (TS_012) Checkout Functionality | Verify other perks like discount codes and giftcards can be applied to the order in checkout page | Open the Website URL https://us.shein.com/ and login | 1. Go to the checkout page 2. Apply discount odes or wallet codes in relevant fields | Not Applicable | The webpage should have options to apply discount codes and giftcards | Working as mentioned in the Expected Result section | P5 | PASS
TC_WL_012 | (TS_012) Checkout Functionality | Verify user cannot proceed to the payment page from the checkout page without selecting a payment method | Open the Website URL https://us.shein.com/ and login | 1. Go to the checkout page 2. Click on proceed to payment without selecting any payment method | Not Applicable | User should not be able to navigate to the payment page without selecting a payment method | Working as mentioned in the Expected Result section | P6 | PASS
TC_WL_013 | (TS_012) Checkout Functionality | Verify adding multiple products to the checkout at the same time | Open the Website URL https://us.shein.com/ and login | 1. Select several products from add to cart 2. Click proceed to checkout | Not Applicable | User should be able to add multiple products simultaneously to the checkout | Working as mentioned in the Expected Result section | P2 | PASS
TC_WL_014 | (TS_012) Checkout Functionality | Verify selecting the Paypal payment method navigates the user to the paypal webpage | Open the Website URL https://us.shein.com/ and login | 1. Go to the checkout page 2. Select the paypal payment method and click continue | Not Applicable | The user should be taken to the paypal webpage | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_015 | (TS_012) Checkout Functionality | Verify selecting the VISA/ debit card navigates the user to card information webpage | Open the Website URL https://us.shein.com/ and login | 1. Go to the checkout page 2. Select the VISA/debit card payment method and click continue | Not Applicable | The user should be taken to the card information page where they can onput their card details | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_016 | (TS_012) Checkout Functionality | Verify proper breadcrumbs are displayed on top of the page for the checkout option | Open the Website URL https://us.shein.com/ and login | 1. Go to the checkout page 2. Check the breadcrumbs on the top corner of the webpage | Not Applicable | The breadcrumbs should be displayed properly | Working as mentioned in the Expected Result section | P1 | PASS
TC_WL_017 | (TS_012) Checkout Functionality | Verify navigating to Checkout page when there are no products added to the Shopping Cart | Open the Website URL https://us.shein.com/ and login | 1. Go to any product details page 2. Check to see if there are any items in the shopping cart | Not Applicable | User should not be able to navigate to the checkout page when there are no products in the shopping cart | Working as mentioned in the Expected Result section | P8 | PASS
TC_WL_018 | (TS_012) Checkout Functionality | Verify the UI of 'Checkout' functionality | Open the Website URL https://us.shein.com/ and login | Check the Ui of the 'Checkout' page | Not Applicable | The Ui of the webpage should adhere to the guidelines of the SRS document | Working as mentioned in the Expected Result section | P9 | PASS
TC_WL_019 | (TS_012) Checkout Functionality | Verify the 'Checkout' functionality in all the supported environments and browsers | Open the Website URL https://us.shein.com/ and login | Check the 'Checkout' page in all the supported environments and browsers | Not Applicable | The Checkout page should work in all suppoted environments and browsers | Working as mentioned in the Expected Result section | P10 | PASS

## Contact Us
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Bug Screenshot | Comments
<< Test Scenarios
TC_WL_001 | (TS_013) Contact Us Functionality | Verify navigating to Contact page from the Homepage | Open the Website URL https://us.shein.com/ and login | 1. Go to the bottom of the homepage 2. Under the customer Care section, click on Contact Us | Not Applicable | User should be able to navigate to Contact Us page from the homepage | Working as mentioned in the Expected Result section | P1 | PASS
TC_WL_002 | (TS_013) Contact Us Functionality | Verify whether the required details and fields are displayed in the 'Contact Us' page | Open the Website URL https://us.shein.com/ and login | 1. Go to the bottom of the homepage 2. Under the customer Care section, click on Contact Us 3. Check different sections in the page | Not Applicable | Required details and fields are displayed in the 'Contact Us' page | Working as mentioned in the Expected Result section | P2 | PASS
TC_WL_003 | (TS_013) Contact Us Functionality | Verify the FAQ section in the Contact Us page | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer care page 2. Check each of the FAQ sections | Not Applicable | The FAQ section should be working properly | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_004 | (TS_013) Contact Us Functionality | Verify text can be input in the bot section of customer service | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer care page 2. Click on the customer service button. 3. Type a text for the bot 4. Press Enter | Not Applicable | User should be able to send text to the bot and get a relevant reply | Working as mentioned in the Expected Result section | P2 | PASS
TC_WL_005 | (TS_013) Contact Us Functionality | Verify the questions in the FAQ section are catagorized in the appropriate catagory | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer care page 2. Check each of the FAQ question are catagorized in their appropriate section | Not Applicable | The FAQ questions should be put in their appropriate sections | Working as mentioned in the Expected Result section | P2 | PASS
TC_WL_006 | (TS_013) Contact Us Functionality | Verify clicking on view more takes the user to support page with more FAQ | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer care page 2. In the FAQ section click in view more | Not Applicable | User should be taken to a new page with more FAQ | Working as mentioned in the Expected Result section | P2 | PASS
TC_WL_007 | (TS_013) Contact Us Functionality | Verify the search option in support page is working properly | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer care page 2. In the FAQ section click in view more | Not Applicable | The search bar in the support page should be working properly | Working as mentioned in the Expected Result section | P2 | PASS
TC_WL_008 | (TS_013) Contact Us Functionality | Verify the answers are appropriate and relevant to their questions | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer care page 2. CHeck the answers to the FAQ | Not Applicable | The answers to the FAQ should be precise and relevant | Working as mentioned in the Expected Result section | P2 | PASS
TC_WL_009 | (TS_013) Contact Us Functionality | Verify the like and dislike buttons underneath each question and answer is working properly | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer care page 2. In the FAQ section click in view more 3. In the support page click on the like or dislike button | Not Applicable | User should be able to like and dislike or change their reaction | User cannton change their reaction. Once a like or a dislike is given, it is fixed | P1 | FAIL | Like and dislike can't be changed
TC_WL_010 | (TS_013) Contact Us Functionality | Verify the customer service button working properly and sending the user to the correct URL | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer care page 2. Click on the costomer service button | Not Applicable | User should go to a new URL for customer services | Working as mentioned in the Expected Result section | P2 | PASS
TC_WL_011 | (TS_013) Contact Us Functionality | Verify communication with the customer service bot is informational | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer care page 2. Click on the customer service button. 3. Click on any of the options displayed 4. Check if the reply from the bot is relevant or not | Not Applicable | User should be able to navigate to Contact Us page from the homepage | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_012 | (TS_013) Contact Us Functionality | Verify the example questions in customer service are working correctly with proper UI | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer care page 2. Click on the customer service button. 3. Click on any of the questions 4. Check the UI of the page | Not Applicable | The questions should give appropriate answers using proper styling and UI | When hovering over a question that same question pops up | P3 | FAIL | UI problem
TC_WL_013 | (TS_013) Contact Us Functionality | Verify the video beneath the customer service button is starting properly in the page | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer care page 2. Click play button on the video | Not Applicable | The video should start playing in the page without redirecting the user to any other URL | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_014 | (TS_013) Contact Us Functionality | Verify the video playback is smooth and other relevant factors are functional | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer care page 2. Click play button on the video 3. Check the video playback is smooth with options for volume and playback speed change | Not Applicable | The video playback should be smooth with options for volume and playback speed change | Working as mentioned in the Expected Result section | P1 | PASS
TC_WL_015 | (TS_013) Contact Us Functionality | Verify the Facebook messenger button takes the user to the appropriate URL | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer care page 2. Click on the facebook icon to go to messenger page of the customer care | Not Applicable | The user should redirected to the messenger URL of the customer care | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_016 | (TS_013) Contact Us Functionality | Verify an the user can contact the customer care using the email provided | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer care page 2. Click on the email and copy it. 3. Use that email address to send an email to the customer care | Not Applicable | User should be able to communicate with the customer care using email address | Working as mentioned in the Expected Result section | P1 | PASS
TC_WL_017 | (TS_013) Contact Us Functionality | Verify the Breadcrumb of 'Contact Us' page | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer care page 2. Check the breadcrumbs on the top | Not Applicable | User should be able to navigate to Contact Us page from the homepage | Working as mentioned in the Expected Result section | P1 | PASS
TC_WL_018 | (TS_013) Contact Us Functionality | Verify the Page URL, Page Heading and Page Title of 'Contact Us' page | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer care page 2. Check the URL, heading and title of the page | Not Applicable | The page url, heading and title should be correct | Working as mentioned in the Expected Result section | P1 | PASS
TC_WL_019 | (TS_013) Contact Us Functionality | Verify the UI of 'Contact Us' page functionality | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer care page 2. Check the user interface(UI) | Not Applicable | The Ui of the webpage should adhere to the guidelines of the SRS document | Working as mentioned in the Expected Result section | P1 | PASS
TC_WL_020 | (TS_013) Contact Us Functionality | Verify the 'Contact Us' page functionality in all the supported environments and browsers | Open the Website URL https://us.shein.com/ and login | Go to the customer care page in different browsers and environments | Not Applicable | User should be able to navigate to Contact Us page from the homepage | Working as mentioned in the Expected Result section | P1 | PASS

## Customer Service
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Bug Screenshot | Comments
<< Test Scenarios
TC_WL_001 | (TS_014) Customer Service Functionality | Verify navigating to Customer Service page from the Homepage | Open the Website URL https://us.shein.com/ and login | On the top right of the home page click on the customer service icon | Not Applicable | User should be able to navigate to customer service page from the homepage | Working as mentioned in the Expected Result section | P1 | PASS
TC_WL_002 | (TS_014) Customer Service Functionality | Verify the chat option with the bot in the customer service page | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer service page 2. In the chat option write any text 3. Check the reply of the bot | Not Applicable | The bot should be able to reply to the user | Working as mentioned in the Expected Result section | P2 | PASS
TC_WL_003 | (TS_014) Customer Service Functionality | Verify the history option in chat working properly | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer service page 2. Click on the check history option in the chat box 3. Check the chat history | Not Applicable | User should be able to get the chat history with the bot on their previous encounter | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_004 | (TS_014) Customer Service Functionality | Verify clicking a quick question enables the bot to give the proper answer | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer service page 2. Click on one of the questions on the right side of the chat 3. Check the reply of the bot | Not Applicable | User should get relevant answer based on the question | Working as mentioned in the Expected Result section | P4 | PASS
TC_WL_005 | (TS_014) Customer Service Functionality | Verify giving positive feedback or negative feedback to the reply of the bot | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer service page 2. Click on one of the questions on the right side of the chat 3. Give positive or negative feedback to the replu using the like and dislike buttons | Not Applicable | User should be able to give positive or negative feedback to the answer by the bot and the bot should reply accordingly | Working as mentioned in the Expected Result section | P5 | PASS
TC_WL_006 | (TS_014) Customer Service Functionality | Verify clicking on the switch button changes the quick questions | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer service page 2. Click on the switch button on the right side of the chat | Not Applicable | The quick questions section should alter the questions | Working as mentioned in the Expected Result section | P6 | PASS
TC_WL_007 | (TS_014) Customer Service Functionality | Verify clicking on a catagory results the bot to give relevant answers in that catagory | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer service page 2. Click on one of the catagories on the right side of the chat | Not Applicable | The user should get relevant answers in that catagory | Working as mentioned in the Expected Result section | P7 | PASS
TC_WL_008 | (TS_014) Customer Service Functionality | Verify the UI of 'Customer Service' page functionality | Open the Website URL https://us.shein.com/ and login | 1. Go to the customer servicepage 2. Check the user interface(UI) | Not Applicable | The Ui of the webpage should adhere to the guidelines of the SRS document | Working as mentioned in the Expected Result section | P1 | PASS
TC_WL_009 | (TS_014) Customer Service Functionality | Verify the Page URL, Page Heading and Page Title of 'Customer Service' page | Open the Website URL https://us.shein.com/ and login | 1. Go to the 'Customer Service' page 2. Check the URL, heading and title of the page | Not Applicable | The page url, heading and title should be correct | Working as mentioned in the Expected Result section | P1 | PASS
TC_WL_010 | (TS_014) Customer Service Functionality | Verify the Customer service page functionality in all the supported environments and browsers | Open the Website URL https://us.shein.com/ and login | Go to the Customer service page in different browsers and environments | Not Applicable | User should be able to navigate toCustomer service page from the homepage | Working as mentioned in the Expected Result section | P5 | PASS

## Global
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Bug Screenshot | Comments
<< Test Scenarios
TC_WL_001 | (TS_015) Global Functionality | Verify navigating to global settings functionality from homepage | Open the Website URL https://us.shein.com/ and login | 1. Go to the top-right of the homepage 2. Click the global icon | Not Applicable | User should be able to navigate to global settings from the home page | Working as mentioned in the Expected Result section | P1 | PASS
TC_WL_002 | (TS_015) Global Functionality | Check the currency dropdown menu of the global settings | Open the Website URL https://us.shein.com/ and login | 1. Go to the global icon on the home page 2. Click the drop-down menu of currency | Not Applicable | User should be able to select any currency that they want to trade with | Working as mentioned in the Expected Result section | P2 | PASS
TC_WL_003 | (TS_015) Global Functionality | Verify changing the language to anything else apart from English | Open the Website URL https://us.shein.com/ and login | 1. Go to the global icon on the home page 2. Select the language of your choice | Not Applicable | User should be able to change the language to anything else apart from English | Working as mentioned in the Expected Result section | P3 | PASS
TC_WL_004 | (TS_015) Global Functionality | Verify changing the currency from USD to other international currencies | Open the Website URL https://us.shein.com/ and login | 1. Go to the global icon on the home page 2. Click the drop-down menu of currencies 3. Select the currency of your choice | Not Applicable | User should be able to change the currency from USD to other international currencies | Working as mentioned in the Expected Result section | P4 | PASS
TC_WL_005 | (TS_015) Global Functionality | Verify changing the website to international version from US version | Open the Website URL https://us.shein.com/ and login | 1. Go to the global icon on the home page 2. Click the international site link | Not Applicable | User should be able to change the website to international version from US version | Working as mentioned in the Expected Result section | P5 | PASS
TC_WL_006 | (TS_015) Global Functionality | Verify changing back the website to US version from international version | Open the Website URL https://us.shein.com/ and login | 1. Go to the global icon on the home page 2. Click the US site link | Not Applicable | User should be able to change back the website to US version from international version | There is no option available to change back to US site version once the user has shifted to international site version | P6 | FAIL | No change back option
TC_WL_007 | (TS_015) Global Functionality | Verify the UI of the website remains unchanged after it changes the language | Open the Website URL https://us.shein.com/ and login | 1. Go to the global icon on the home page 2. Select the language of your choice 3. Check the UI of the page | Not Applicable | The page UI should be very similar the original English version of the page | Working as mentioned in the Expected Result section | P7 | PASS
TC_WL_008 | (TS_015) Global Functionality | Verify the UI of the website remains unchanged after it changes to international version from US version | Open the Website URL https://us.shein.com/ and login | 1. Go to the global icon on the home page 2. Click the international site link | Not Applicable | The site UI should remain similar for both the US and international version | Working as mentioned in the Expected Result section | P8 | PASS
TC_WL_009 | (TS_015) Global Functionality | Verify the change in currency is reflected all over the website in the product details | Open the Website URL https://us.shein.com/ and login | 1. Go to the global icon on the home page 2. Click the drop-down menu of currencies 3. Select the currency of your choice 4. Go to a product details page and check the currency values | Not Applicable | The currency in the product detils page should change to the one the user selected | Working as mentioned in the Expected Result section | P9 | PASS
TC_WL_010 | (TS_015) Global Functionality | Verify the website can be accessed all over the world using VPN | Open the Website URL https://us.shein.com/ and login | 1. Access the website using a Virtual Protocol Network(VPN) 2. Select network of different countries and access the website | Not Applicable | The website should be accessible from from parts of the world | Working as mentioned in the Expected Result section | P10 | PASS
TC_WL_011 | (TS_015) Global Functionality | Verify the global functionality in all available browsers and environment | Open the Website URL https://us.shein.com/ and login | Go to the global functionality using all available environments and browsers | Not Applicable | User should be able to use the global functionality using all available environments and browsers | Working as mentioned in the Expected Result section | P11 | PASS